## Sheet1
Task | Start Date | Duration | End Date | Status
Choose Data set | 2013-03-28 | 7 | 2013-04-04 | Complete-EB
Choose visualization library | 2013-03-28 | 7 | 2013-04-04 | Complete-EB
Project Plan -EB | 2013-04-05 | 1 | 2013-04-06 | Complete-EB
leancanvas blueprint -AK | 2013-04-05 | 3 | 2013-04-08 | Complete-AK
Create mockup -EB | 2013-04-06 | 1 | 2013-04-07 | Complete-EB
Research D3.js | 2013-04-04 | 7 | 2013-04-11 | Complete-EB
Research mongoDB -EB | 2013-04-06 | 2 | 2013-04-08 | Complete-EB
Research node.js -EB | 2013-04-08 | 2 | 2013-04-10 | Complete-EB
Research JS -AK | 2013-04-08 | 3 | 2013-04-11 | In progress
Research HTML -AK | 2013-04-11 | 2 | 2013-04-13 | unknown
Research CSS -AK | 2013-04-13 | 2 | 2013-04-15 | unknown
Choose data set data points | 2013-04-08 | 1 | 2013-04-09 | Complete
Create data set CSV- EB | 2013-04-22 | 4 | 2013-04-26 | Complete
Implement mongoDB -EB | 2013-04-08 | 7 | 2013-04-15 | Complete-EB
Implement node.js -EB | 2013-04-08 | 7 | 2013-04-15 | Complete-EB
Create basic container webpage -AK | 2013-04-15 | 1 | 2013-04-16 | Complete-EB
Implement template D3.js visualization | 2013-04-15 | 1 | 2013-04-16 | Complete-EB
Test basic webpage functionality - AK | 2013-04-16 | 1 | 2013-04-17 | Complete-EB
Test basic data set CR[UD] - EB | 2013-04-17 | 2 | 2013-04-19 | Complete-EB
Test basic visualzation population | 2013-04-17 | 2 | 2013-04-19 | Complete-EB
Fully implement visualization | 2013-04-19 | 7 | 2013-04-26 | Complete-EB
Test visualization interaction | 2013-04-19 | 7 | 2013-04-26 | Complete-EB
Polish webpage HTML, CSS | 2013-04-26 | 7 | 2013-05-03 | Complete-EB
Post final product | 2013-05-03 | 7 | 2013-05-10 | Complete-EB
2013-05-17
Formulas:
End Date = SUM([Start Date],[Duration])
Note on E14: Eric Bauer: Create single mode valued matrix. Issue: must create PLSQL script for data compilation